## Project Info
Construction Quality Control Checklist
Field inspection record — 30 inspection points
Project name
Project / contract number
Client / owner
Contractor
Area / system / work package
Activity inspected
Governing ITP number and revision
Drawing number and revision
Specification reference
Checklist document number
Checklist revision
Inspection date
Inspector (name / title)
Witnessed by (client / third party)
How to use
1. Complete this sheet before going to the work face. Blue / yellow cells are inputs.
2. On the Checklist sheet, delete rows that do not apply and add discipline-specific rows that do.
3. Enter the governing ITP line, drawing revision or specification clause against every row you keep.
4. Record the measured value, not only the verdict. Status is C (conforming), NC (non-conforming) or N/A.
5. Every NC row needs a deficiency reference (NCR or punch-list number) before the checklist is signed.
6. Sign, date and file the completed checklist against the system, then index it into the turnover package.
This template is a starting point, not a controlled document. Bring it under your own document control,
and align it to the contractual requirements and project specifications, which always govern.

## Checklist
# | Inspection item | Governing reference (ITP line / drawing rev / spec clause) | Acceptance criteria | Status | Observation / measurement (with units) | Deficiency ref (NCR / punch) | Inspector | Date | Evidence ref (photo / report / cert)
DOCUMENTATION AND READINESS
1 | Drawings, specifications and approved ITP at the work face are the current revision; superseded copies withdrawn
2 | Method statement / work procedure approved and communicated to the crew performing the activity
3 | Personnel competency and certification records current (welders, NDT, surveyors, riggers, electrical testers)
4 | Measuring and test equipment within calibration; certificate identifiers recorded on this record
5 | Permits, notifications and client / authority witness invitations issued within the required notice period
6 | Previous-stage inspection records closed out; deficiencies cleared or formally accepted
MATERIALS RECEIVING AND STORAGE
7 | Delivered material matches purchase order, approved vendor list and specified grade on the drawing
8 | Mill / batch certificates supplied, legible and traceable to heat, batch or lot markings
9 | No transit damage, corrosion, contamination or coating breakdown beyond acceptance limits
10 | Storage off-ground, protected, segregated by grade; shelf-life products dated and within life
11 | Identification and traceability markings transferred and preserved when material is cut, formed or issued
EARTHWORKS AND FOUNDATIONS
12 | Excavation dimensions, levels and side-slope stability match IFC drawings and geotechnical requirements
13 | Subgrade inspected and accepted; proof-rolling or bearing verification recorded where specified
14 | Fill material, layer thickness and compaction results meet specified density; test locations plotted
15 | Underground services, sleeves, ducts and buried protection installed, surveyed and photographed before backfill
CONCRETE WORKS
16 | Formwork set to line, level and dimension; braced, clean and treated with approved release agent
17 | Reinforcement size, grade, spacing, lap length, cover and support verified to drawing and bar bending schedule
18 | Embedded items (anchor bolts, base plates, conduits, waterstops, sleeves) located, secured and surveyed before pour release
19 | Approved mix design, delivery ticket, slump, air content and temperature checked; test cylinders cast and identified
20 | Curing method, duration and protection applied as specified; formwork striking respects specified strength gain
STRUCTURAL STEEL AND WELDING
21 | Fit-up, alignment, root gap and joint preparation conform to the approved welding procedure before welding starts
22 | Welding by qualified welders to an approved procedure; parameters, consumables and preheat recorded in the weld log
23 | Visual inspection and specified NDE completed; reports referenced to weld identifiers on the drawing
24 | Bolted connections installed to the specified assembly; pretension or turn-of-nut verification recorded where required
PIPING, MECHANICAL AND ELECTRICAL
25 | Piping and equipment installation matches isometrics and GA drawings, including supports, slopes, orientation, clearances
26 | Pressure testing, flushing and cleanliness verification completed to specified parameters; signed test packs retained
27 | Cable installation, terminations, grounding, segregation and labelling verified; continuity, IR and functional tests recorded
COATINGS, CLOSE-OUT AND TURNOVER
28 | Surface preparation, ambient conditions, coating system, WFT/DFT and holiday testing meet the coating specification
29 | Non-conformances and punch-list items raised, dispositioned, corrected, re-inspected and formally closed with evidence
30 | Completed checklists, test reports, certificates and as-built markups compiled, indexed and handed over per system
SUMMARY
Items conforming (C)
Items non-conforming (NC)
Items not applicable (N/A)
Items not yet assessed
Open deficiencies without a reference
SIGN-OFF
Inspector (name, signature, date)
Client / third-party witness (name, signature, date)
Accepted by (name, signature, date)

## Status key
Conformance status key
Code | Meaning | How to use it
C | Conforming | Checked against the stated acceptance criteria and found acceptable. Record the measured value, not only the verdict.
NC | Non-conforming | Does not meet the acceptance criteria. Raise an NCR or punch-list item and enter the reference in column G before signing.
N/A | Not applicable | The item does not apply to this scope. State why in the observation column so the omission is explained at review.
Source: Jags Assurance Inc., construction quality control checklist template, jagsassurance.com