## ITP
Inspection and Test Plan (ITP)
Template by Jags Assurance Inc. — jagsassurance.com. Free to adapt; place under your own document control before issue.
Project / contract: |  |  | Client:
Supplier / vendor: |  |  | Purchase order no.:
ITP document no.: |  |  | Revision / date:
Prepared by: |  |  | Approved by (client):
Item No. | Activity / operation | Reference document (spec, drawing, code clause) | Acceptance criteria | Inspection / test method | Frequency / extent | Responsibility | Contractor | Vendor | TPI | Client | Verifying record | Remarks
1.0 | Document review — WPS / PQR / WQT | AWS D1.1 cl.4 / ASME IX | Qualified and approved before production | Document review | 100% | QA/QC Manager | R | R | R | W | Approved WPS/PQR register
2.0 | Material receipt and identification | PO, MTR, EN 10204 3.1 | Heat no. traceable, certificate matches order | Visual / document check | 100% | QC Inspector | H | R | W |  | Material receiving report
3.0 | Fit-up inspection | Approved drawing rev. | Root gap, alignment, bevel within tolerance | Visual / measurement | 100% of joints | QC Inspector | H | R | W |  | Fit-up report
4.0 | Welding — in-process | WPS, AWS D1.1 | Preheat, interpass, parameters within WPS | Visual / monitoring | Random 10% | CWI | W | R | W |  | In-process weld log
5.0 | Visual weld inspection | AWS D1.1 Table 6.1 | No cracks, undercut within limits | VT by CWI | 100% | CWI | H | R | W |  | VT report
6.0 | NDT (RT / UT / MT / PT) | ASME V / client NDT plan | Per acceptance code and class | RT/UT/MT/PT | Per spec % | NDT Level II | R | R | W | S | NDT reports
7.0 | Dimensional inspection | Approved drawing rev. | Dimensions within stated tolerance | Measurement | 100% | QC Inspector | H | R | W |  | Dimensional report
8.0 | Surface preparation | SSPC-SP10 / ISO 8501-1 | Sa 2.5, profile 40–75 microns | Visual / profile gauge | Each blast lot | Coating Inspector | H | R | W |  | Blast inspection record
9.0 | Coating application and DFT | Paint spec / manufacturer TDS | DFT per SSPC-PA2, no holidays | DFT gauge / holiday test | Per SSPC-PA2 | Coating Inspector | H | R | W |  | DFT report
10.0 | Pressure / leak test | ASME B31.3 cl.345 | Hold pressure, no leakage or permanent set | Hydro / pneumatic | 100% | QC Inspector | H | R | H | W | Pressure test certificate
11.0 | Functional / factory acceptance test | FAT procedure rev. | Meets datasheet performance | FAT | 100% | Project Engineer | W | R | W | W | FAT report
12.0 | Final inspection and release | ITP, punch list | All punch items cleared, NCRs closed | Visual / document | 100% | QA/QC Manager | H | R | H | W | Release note / CoC
13.0 | Preservation, packing and marking | Packing spec | Protected, marked, preservation applied | Visual | 100% | Warehouse / QC | W | R | W |  | Packing list
14.0 | Turnover documentation / MRB | MRB index | Complete, indexed, legible, traceable | Document review | 100% | Document Control | R | R | R | W | Manufacturing Record Book
Intervention code legend
H | Hold point — work may not proceed past this point until the party has attended and released it in writing.
W | Witness point — the party is notified and may attend; work may proceed if they do not attend after due notice.
S | Surveillance / monitoring — periodic unannounced verification of the activity.
R | Review of records only — no physical attendance required.